## pg
State Ministry of Rural and Sports Infrastructure Promotion
Rural and playground renovation program -2021
Progress
District-Kandy
SN | DS Division | GN Division | Local Government | Project Name | Project | Implemented by | Allocation Released by the Ministry | Date of Release | Estmated Amount | Date when DS Received the Allocations | Contract amount (Rs.) | Physical Progress | [7 empty] | Financial Progress |  | Time
[12 empty] | A | B | C | D | E | F | G | H | Cost | Bill in Hand | Date of commencement of work | Date of completion of work
1 | Thumpane | Udalagama 309 | Galagedara | Volleyball Stadium at Galagedara Public Ground | Developmentof outdoor volleyball court | A | 1500000 | 2021-03-30 | 1500000 | 2021.04.06 | 1470588.24 | Physical Progress H: √; Financial Progress Cost: 1470588.24 | _ | 2021.05.21 | 2021.07.17
|  | Physical Progress |  |  | Operaions & Maintenance
|  | A- Not estimated |  |  | A - අදාළ පළාත් පාලන ආයතනය විසින්
|  | B-estimated |  |  | B-අදාළ ප්‍රා.ලේ. කාර්යාලය විසින්
|  | C-Date of signing the agreement |  |  | C-ප්‍රා.ලේ.ගේ. අධීක්ෂණය යටතේ ක්‍රීඩා සමාජයක් විසින්
|  | D- Work has started and less than 25% progress |  |  | D- වෙනත්
E- With 26% -50% progress
F- With 51% -75% progress
G-More than 76% progress
H - වැඩ අවසන්