## Animal husbandry
Saubhagya Production Villages - Kandy District
Progress on 2021.12.31
DS Division - Thumpane GN Division :- Kuragama,Nikathenna,Udahenepola,Kaluwana,Udapitiya
Name of The Project :- Sasiri Saubhagya Animal Husbandry Village Number of beneficiaries :- 74
Activity | Approved Number of equipment / animals | Number of equipment / animals Provided | Total Estimation | Community contribution Rs. | Approved Government Contribution Rs. | Physical Progress | [9 empty] | Financial Progress |  | Actual Cost
[6 empty] | A | B |  |  |  | C | D | E | F | G | Community contribution Rs. | Approved Government Contribution Rs.
[7 empty] | B1 | B2 | B3 | B4
Providing Poultry Chicks (Hens) | 1125 | 900 |  | 263125 | 263125 | [9 empty] | √ | 202500 | 202500 | 405000
|  | Transport | [14 empty] | 3400 | 3400
Providing Village Poultry Chicks (Hens) | 150 | 150 |  | 42500 | 42500 | [9 empty] | √ | 30000 | 30000 | 60000
Grass cultivation | 24000 | Cuttings 16800 |  |  | 247500 | [9 empty] | √ |  | 53400 | 53400
|  | Transport | [14 empty] | 3000 | 3000
Construction of cattle shed | 9 | Amano Sheets 8 " - 40 |  | 675000 | 675000 | [9 empty] | √ |  | 107200 | 107200
|  | Cement - 64 |  | 92800 | 92800 | [9 empty] | √ |  | 92800 | 92800
Construction of Poultry Cages | 25 | Amano Sheets 8" &10 " - 203 |  | 625000 | 625000 | [11 empty] | 575880 | 575880
|  | Cement- 68 | [14 empty] | 98600 | 98600
|  | Chicken nets - Feet 1208 | [12 empty] | √ |  | 169120 | 169120
Providing grass chopping/cutting Machines | 5 | 1 |  | 90000 | 360000 | [9 empty] | √ |  | 260370 | 260370
Purchase of milk collection jars |  | 8 | [12 empty] | √ |  | 67600 | 67600
Sealer Machine | 10 | 9 |  | 70000 | 280000 | [9 empty] | √ |  | 53100 | 53100
Shovel | 10 | 69 | [12 empty] | √ |  | 82800 | 82800
Plates (Construction) |  | 2 | [12 empty] | √ |  | 9000 | 9000
Milk Toffee Stencil |  | 2 | [12 empty] | √ |  | 7500 | 7500
Egg packaging |  | 384 | [12 empty] | √ |  | 75852 | 75852
Poultry Water Feeding Buckets |  | 155 | [12 empty] | √ |  | 65100 | 65100
Poultry Feeding Buckets |  | 156 | [12 empty] | √ |  | 109200 | 109200
Water Spraying Buckets | 10 | 71 | [12 empty] | √ |  | 53250 | 53250
R.G.G Padma Construction of Poultry Hut | [14 empty] | √ |  | 60000 | 60000
R.G.Sshanthi Mala Construction of Poultry Hut | [14 empty] | √ |  | 60000 | 60000
D.D Dingiri Amma Construction of Poultry Hut | [14 empty] | √ |  | 40000 | 40000
Wheel Barrow | 10 | 68 | [12 empty] | √ |  | 404600 | 404600
Polythene | 10 | 45kg | [12 empty] | √ |  | 14400 | 14400
Name Boards | [14 empty] | √ |  | 17500 | 17500
Providing equipment for milk toffee production |  |  |  | 25000 | 25000 | [9 empty] | √
Training Programs |  |  |  |  | 75000 | [9 empty] | √ |  | 75000 | 75000
Additional provisions |  | Village Poultry Chicks 460 |  | 170000 | 170000 | [9 empty] | √ | 153749.5 | 198150.5 | 351900
|  | Layer Poultry Chicks 425 | [12 empty] | √ | 100937.5 | 100937.5 | 201875
|  | Transport | [12 empty] | √ |  | 4400
|  | Amano Sheets 8"&10 "-304 | [12 empty] | √ |  | 950060 | 950060
|  | Buying a dairy cow | [12 empty] | √ | 750000 | 75000 | 150000
|  | Chicken nets - Feet 1725 | [12 empty] | √ |  | 241500 | 241500
Administrative cost 1% |  |  |  |  | 108041.42 | [11 empty] | 68483
Total |  |  |  | 2053425 | 4429703 | [10 empty] | 1237187 | 4429703 | 4919007
Physical progress
A - Estimates are being / to be prepared/Idefying Locations/applicatins are beeing called
B-1= Estimates Approved Procument Documents Prepared, B-2= Procurement Noticed Issued , B-3= Procurement Document Received , B-4= Procument Awarded
C - 1% - 40% Consrtuctions Completed/ Goods,equipments,Material Recevied/Training Programmes Conducted/bills are to be paid
D - Constructions 60% completed /Goods,equipments,Material Recevied/Training Programmes Conducted/bills are to be paid
E - Constructions 80% completed /Goods,equipments,Material Recevied/bills are to be paid
F - Constructions 99% completed /Goods,equipments,Material Recevied/bills are to be paid
G -Constructions 100 % Completed / Goods,equipments,Material hand over /bills paid