## සෞභාගයා ඉදිකිරීම්
Saubhagya Production Village Program
Development of access roads leads to the projects
Progress on 2021.12.31
DS Division :- Thumpane | [18 empty] | other
SN | Project Name | GN Division | Name of the Development Proposal | Allocated Rs | Estimation Rs | Cost Rs | ම්නුම් ඒකකය | Physical Progress (d ) | [9 empty] | Number of beneficiaries
[8 empty] | A | B |  |  |  | C | D | E | F | G
[9 empty] | B1 | B2 | B3 | B4
1 | Animal Production | Nikathenna | Development of Galagedarawatta Nikathenna Road | 700000 | 698097.48 | 696585.36 | [10 empty] | √ | 156 | Bill in hand
2 |  |  | Development of Galagedarawatta Galwetikanda Road | 500000 | 498364.84 | 497560.97 | [10 empty] | √ | 63 | Bill in hand
3 |  | Kuragama | Development of Kuragama Colony Road | 900000 | 880629 | 895609.75 | [10 empty] | √ | 62 | Bill in hand
4 |  | Udahenepola | Development of the road from Dewalkana road to the rubber Estate | 400000 | 381243.9 | 388852.66 | [10 empty] | √ | 68 | Bill in hand
5 |  | Udapitiya | Development of the road near Small Bambara Tree Junction with Drainage System | 500000 | 487804.88 | 497560.97 | [10 empty] | √ | 12 | Bill in hand
6 | Mushroom | Medagoda Ihala | Development of Madakoladeniya Thittakohe Road | 500000 | 489298.02 | 497560.97 | [10 empty] | √ | 64 | Bill in hand
7 |  | Kaluwana | Development of the road near the house of Mrs. Shiromi Amarasinghe | 500000 | 466944.14 | 476283.07 | [10 empty] | √ | 101 | Bill in hand
8 |  | Naranwala | Development of the road from near the Grama Niladhari office to Yakammale | 700000 | 682926.83 | 695851.15 | [10 empty] | √ | 62 | Bill in hand
9 |  | Uduwa | Development of Uduwa Goda Road | 800000 | 780804.88 | 796097.55 | [10 empty] | √ | 151 | Bill in hand
10 |  | Palukopiwatta | Development of the road from near the house of Mr. Kalu Piyadasa to the house of Mr. Attanayake | 500000 | 489293.02 | 487804.88 | [10 empty] | √ | 61
|  |  |  | 6000000 | 5855406.99 | 5929767.33 | [10 empty] | 10 | 800
Physical progress
A - Estimates are being / to be prepared/Idefying Locations/applicatins are beeing called
B-1= Estimates Approved Procument Documents Prepared, B-2= Procurement Noticed Issued , B-3= Procurement Document Received , B-4= Procument Awarded
C - 1% - 40% Consrtuctions Completed/ Goods,equipments,Material Recevied/Training Programmes Conducted/bills are to be paid
D - Constructions 60% completed /Goods,equipments,Material Recevied/Training Programmes Conducted/bills are to be paid
E - Constructions 80% completed /Goods,equipments,Material Recevied/bills are to be paid
F - Constructions 99% completed /Goods,equipments,Material Recevied/bills are to be paid
G -Constructions 100 % Completed / Goods,equipments,Material hand over /bills paid