## Mashroom
Saubhagya Production Villages - Kandy District
Progress on 2021.12.31
DS Division - Thumpane GN Division Medagoda Ihala/Palukopiwatta/Kaluwana/Naranwala/Uduwa/Hithgoda Walpola/Haddapitiya/henegama/Minigamuwa/Ambagahahena
Project Name :- Mashroom Production Number of beneficiaries :- 29
Activity | Approved Number of equipment / animals | Number of equipment / animals Provided | Total Estimation | Community contribution Rs. | Approved Government Contribution Rs. | Physical Progress | [9 empty] | Financial Progress |  | Actual Cost
[6 empty] | A | B |  |  |  | C | D | E | F | G | Community contribution Rs. | Approved Government Contribution Rs.
[7 empty] | B1 | B2 | B3 | B4
Construction of mushroom houses | 15 | Insect repellent net square feet 17676 |  | 2250000 | 2250000 | [9 empty] | √ |  | 373000 | 373000
|  | Amano Sheet Feet 8 *396 | [12 empty] | √ |  | 1101480 | 1101480
|  | Amano Sheet Feet 10*12 | [12 empty] | √
|  | Cement Columns 10*102 12*34 | [12 empty] | √ |  | 314160 | 314160
|  | Cement 6 | [12 empty] | √ |  | 8700 | 8700
Cultivation bags | 75000 | 28500 |  | 1500000 | 1500000 | [9 empty] | √ | 285095 | 854905 | 1140000
Purchase of mushroom seed packet making machine | 2 | 1 |  | 400000 | 400000 | [9 empty] | √ |  | 200000 | 200000
Purchase of mushroom sterilization boilers | 1 | 1 |  | 140000 | 140000 | [9 empty] | √ |  | 190000 | 190000
Payment for Mrs. Hemanthi's Mashroom house | [14 empty] | √ |  | 40000 | 40000
Name Boards |  | 1 | [12 empty] | √ |  | 20500 | 20500
Transport (mushroom seed packet making machine & mushroom sterilization boiler) | [14 empty] | √ |  | 14700 | 14700
Polythene Seaer | 15 |  | 1 | 15000 | 15000 | [9 empty] | √ |  | 5950 | 5950
Construction of Mushroom Selling Boutique |  | 1 |  | 1125000 | 1125000 | [9 empty] | √ |  | 453698.1 | 453699.1
|  |  |  | 150000 | 150000 | [9 empty] | √
|  |  |  | 130000 | 130000 | [9 empty] | √
|  |  |  | 15000 | 15000 | [9 empty] | √
|  |  |  | 26250 | 26250 | [9 empty] | √
|  |  |  | 175000 | 175000 | √ | [8 empty] | √
Training Programs |  | 2 |  |  | 75000 | [9 empty] | √ |  | 75000 | 75000
Administrative cost 1.5% |  |  |  |  | 90018.75 | [9 empty] | √ |  | 90018.75 | 90018.75
Total |  |  |  | 5926250 | 6151280.25 | [9 empty] | √ | 285095 | 3742111.85 | 4027207.85
Physical progress
A - Estimates are being / to be prepared/Idefying Locations/applicatins are beeing called
B-1= Estimates Approved Procument Documents Prepared, B-2= Procurement Noticed Issued , B-3= Procurement Document Received , B-4= Procument Awarded
C - 1% - 40% Consrtuctions Completed/ Goods,equipments,Material Recevied/Training Programmes Conducted/bills are to be paid
D - Constructions 60% completed /Goods,equipments,Material Recevied/Training Programmes Conducted/bills are to be paid
E - Constructions 80% completed /Goods,equipments,Material Recevied/bills are to be paid
F - Constructions 99% completed /Goods,equipments,Material Recevied/bills are to be paid
G -Constructions 100 % Completed / Goods,equipments,Material hand over /bills paid