## Mashroom
සෞභාග්‍යා නිෂ්පාදන ගම්මාන වැඩසටහන - මහනුවර දිස්ත්‍රික්කය
2021.12.31 දිනට ප්‍රගතිය
ප්‍රාදේශිය ලේකම් කොට්ඨාසය :- තුම්පනේ මැදගොඩ ඉහළ/පාළුකෝපිවත්ත/කළුවාන/නාරංවල/උඩුව/හිත්ගොඩ වල්පොල/හද්දාපිටිය/හේනේගම පල්කුඹුර/මිනිගමුව/අඹගහහේන
ව්‍යාපෘතියේ නම :- බිම්මල් මල් නිෂ්පාදනය ප්‍රතිලාභීන් සංඛ්‍යාව :- 29
ක්‍රියාකාරකම | අනුමත උපකරණ/සතුන් ප්‍රමාණය | ලබාදුන් උපකරණ/සතුන් ප්‍රමාණය | ව්‍යාපෘතියේ මුළු ඇස්තමේන්තු මුදල රු. | ප්‍රජා දායකත්වය රු. | අනුමත රජයේ දායකත්වය රු. | භෞතික ප්‍රගතිය | [9 empty] | මුල්‍ය ප්‍රගතිය |  | සත්‍ය වියදම රු.
[6 empty] | A | B |  |  |  | C | D | E | F | G | ප්‍රජා දායකත්වය රු. | අනුමත රජයේ දායකත්වය රු.
[7 empty] | B1 | B2 | B3 | B4
බිම්මල් ගෘහ ඉදි කිරීම | 15 | කෘමි විකර්ශණ දැල වර්ග අඩි 17676 |  | 2250000 | 2250000 | [9 empty] | √ |  | 373000 | 373000
|  | අමානෝ තහඩු අඩි 8 *396 | [12 empty] | √ |  | 1101480 | 1101480
|  | අමානෝ තහඩු අඩි 10*12 | [12 empty] | √
|  | සිමෙනිති කණු 10*102 12*34 | [12 empty] | √ |  | 314160 | 314160
|  | සිමෙන්කි 6 | [12 empty] | √ |  | 8700 | 8700
වගා මළු | 75000 | 28500 |  | 1500000 | 1500000 | [9 empty] | √ | 285095 | 854905 | 1140000
බිම්මල් බීජ පැකට් සැදීමේ යන්ත්‍රය මිලදී ගැනීම | 2 | 1 |  | 400000 | 400000 | [9 empty] | √ |  | 200000 | 200000
බිම්මල් ජීවානුහරණය කරන බොයිලර් මිලදී ගැනීම | 1 | 1 |  | 140000 | 140000 | [9 empty] | √ |  | 190000 | 190000
හේමන්ති මහතිමියගේ ගෘහයට ගෙවීම | [14 empty] | √ |  | 40000 | 40000
නාම පුවරුව |  | 1 | [12 empty] | √ |  | 20500 | 20500
ප්‍රවාහනය (බිම්මල් බීජ පැකට් සැදීමේ යන්ත්‍රය හාබිම්මල් ජීවානුහරණය කරන බොයිලර් | [14 empty] | √ |  | 14700 | 14700
පොලිතින් සීලර් | 15 |  | 1 | 15000 | 15000 | [9 empty] | √ |  | 5950 | 5950
බිමිමල් අලෙවිසැල ඉදිකිරීම |  | 1 |  | 1125000 | 1125000 | [9 empty] | √ |  | 453698.1 | 453699.1
|  |  |  | 150000 | 150000 | [9 empty] | √
|  |  |  | 130000 | 130000 | [9 empty] | √
|  |  |  | 15000 | 15000 | [9 empty] | √
|  |  |  | 26250 | 26250 | [9 empty] | √
|  |  |  | 175000 | 175000 | √ | [8 empty] | √
පුහුණු වැඩසටහන් |  | 2 |  |  | 75000 | [9 empty] | √ |  | 75000 | 75000
පරිපාලන වියදම 1.5% |  |  |  |  | 90018.75 | [9 empty] | √ |  | 90018.75 | 90018.75
එකතුව |  |  |  | 5926250 | 6151280.25 | [9 empty] | √ | 285095 | 3742111.85 | 4027207.85
Physical progress
A - Estimates are being / to be prepared/Idefying Locations/applicatins are beeing called
B-1= Estimates Approved Procument Documents Prepared, B-2= Procurement Noticed Issued , B-3= Procurement Document Received , B-4= Procument Awarded
C - 1% - 40% Consrtuctions Completed/ Goods,equipments,Material Recevied/Training Programmes Conducted/bills are to be paid
D - Constructions 60% completed /Goods,equipments,Material Recevied/Training Programmes Conducted/bills are to be paid
E - Constructions 80% completed /Goods,equipments,Material Recevied/bills are to be paid
F - Constructions 99% completed /Goods,equipments,Material Recevied/bills are to be paid
G -Constructions 100 % Completed / Goods,equipments,Material hand over /bills paid